## Work Items
Type | Description | Owner | Status | Link | Notes
Definition | Document deliverables with team. | Zaynab | Done | Refer to Deliverables sheet.
| Setup team work sessions. | Zaynab | Done
Structure | Create Google folder. | Andrew | Done | SynthMed Google Folder
| Add 10 pdfs and one book pdf to Google folder. | Zaynab | Done | SynthMed PDF Folder
| Create GitHub project. | Jay | Done | SynthMed GitHub Project
| Create solution diagram. | Jay | Done | SynthMed Diagram
| Document Orchestrate and SynthMed setup. | Jay | Done | SynthMed Orchestrate Setup
| Setup project spreadsheet. | Jay | Done | Reter to this spreadsheet.
Research | How to access online medical PDFs. | Andrew | Done |  | Zaynab provided example of pubmed API code that extracts articles - extend to download PDFs.
| How to use EndNote if possible (EndNote Basic is free). | Andrew | Done |  | Zaynab mentioned has online search to find papers, PDFs, citations, etc.
| Design/test prompts and compare output across Granite models. | Andrew | Done |  | Use prompt lab to tune prompts for medical domain specificity, citation density, and answer granularity.
| When agent is retrieving info can the citation be generated from metadata. | Andrew
Implementation | Create initial single agent prototype with local pdfs. | Jay | Done
| Add multiple agents split by disease type. | Jay | Done
| Update synthmed*kb yaml description fields. | Zaynab | Done |  | Ensure description fields are sufficient for determining which subagent to invoke.
| Update synthmed main agent yaml text fields and required subagent fields. | Zaynab | Done |  | Fields: description, welcome_content, starter_prompts, instructions, guidelines, chat_with_docs.
| Rewrite import-all.sh implementation for simplification and maintainability. | Alex | Done
| Implement remove-all.sh similar to import-all.sh. | Alex | Done
| Add several additional pdfs so each disease has at least five pdfs. | Zaynab | Done
| Update all kb yaml files to include the additional pdfs. | Jay | Done
| Refine instructions/descriptions in agent(s) to ensure desired responses. | Jay | Done
| Validate output of instructions/descriptions in agent(s) and update as needed. | Zaynab | Done
| Document prompts for each disease and across diseases. | Zaynab | Done |  | e.g. What are shared cellular mechanisms betwen epilepsy, autism, and dementia? Which geners overlapb between autism and rare diseases?
| Use both online pdfs (PubMed?) and local pdfs. | Andrew | Done |  | e.g. Check: https://clinicaltrials.gov/data-api/api. Check: arxiv.org used in IBM example for Quantative Biology.
| Implement code to use both pdf kb and LLM (not one or the other). | Alex | Done |  | e.g. Implement sematic retriever tool on pdfs using LangChain's VectorStoreRetriever, pass to LLM syntheseis tool or prompt template.
| Implement code to ingest, retrieve, synthesize, and validate. | Alex | Done
| Implement Colab notebook. | Jay | Done
| Continue testing disease and across diseases. | Team | Done
Midpoint Demo | Create video demo. | Zaynab | Done
| Document problem and solution. | Zaynab | Done
| Document technology used. | Jay | Done
| Provide code repository link. | Jay | Done
Final Demo | Create video demo. | Zaynab | Done
| Document problem and solution. | Zaynab | Done
| Document technology used. | Jay | Done
| Provide code repository link. | Jay | Done

## Deliverables
Week | Description | Status | Link | Notes
One | Team Charter | Done | SynthMed Team Charter
| Research Plan | Done | SynthMed Research Plan
Two | Empathy Map | Done | SynthMed Empathy Map
| As-Is Scenario Map | Done | SynthMed As-Is Scenario Map
| Needs Statement | Done | SynthMed Needs Statement
Three | To-Be Scenario Map | Done | SynthMed To-Be Scenario Map
| Prioritization Grid | Done | SynthMed Prioritization Grid
| Mockup Prototype | Done | SynthMed GitHub Project
| Solution Feature List | Done | SynthMed Solution Feature List
Four | Setup technical foundation | Done | SynthMed GitHub Project
| Initial implementation of core | Done | SynthMed GitHub Project
Five | Complete initial implementation | Done
Six | Submit midpoint project (demo, desc, tech used, code repo) | Done
Seven | Submit final project (demo, desc, tech used, code repo) | Done

## Team
Role | Responsibilities | Owner | Email | Notes
Team Lead | Coordinates team meetings and ensures project progress. | Zaynab | zaynabshakkour@hotmail.com
Research Lead | Oversees user research and insight synthesis. | Andrew | keeandrew.l@gmail.com
Solution Designer | Guides the design thinking and prototyping process. | Jay | jaywarfield@gmail.com
Code Developer | Code developer utilizing Granite Code Generation. | Alex | althex123@gmail.com
Technical Lead | Manages technical development and tool implementation. | Team | N/A
Communications Lead | Leads final presentation, documentation, and submissions. | Team | N/A